## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Moreen Muthoni Murugi | PDF Report, Scrum Board Management, AI Usage Log,XML Data Parsing , GitHub Setup | m.murugi@alustudent.com
Emna Barezi | XML Parsing, API Server Implementation, Basic Authentication, DSA Implementation, API Documentation, README | e.barezi@alustudent.com
[Name]
[Name]
[Name]
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| XML Data Parsing | Emna Barezi & Moreen Muthoni Murugi | 2026-05-29 | Completed | Yes
| API Server Implementation with all 5 CRUD endpoints | Emna Barezi | 2026-05-29 | Completed | Yes | For Emna: Implemented and tested successfully.
| Basic Authentication and security | Emna Barezi | 2026-05-29 | Completed | Yes | For Moreen's tasks: Reviewed and approved by team.
| DSA linear search and dictionary lookup implementation | Emna Barezi | 2026-05-29 | Completed | Yes
| Team participation sheet | Emna Barezi | 2026-05-30 | Completed | Yes
| Readme file | Emna Barezi | 2026-05-30 | Completed | Yes
| API documentation (api_docs.md) | Emna Barezi | 2026-05-28 | Completed | Yes
| API testing and screenshots | Emna Barezi | 2026-05-28 | Completed | Yes
| PDF Report writing and formatting | Moreen Muthoni Murugi & Emna Barezi | 2026-05-30 | Completed | Yes
| API Documentation | Moreen Muthoni Murugi | 2026-05-30 | Completed | Yes
| GitHub repository initial setup | Moreen Muthoni Murugi | 2026-05-30 | Completed | Yes
| Scrum Board | Moreen Muthoni Murugi | 2026-05-30 | Completed | Yes
| AI Usage Log | Moreen Muthoni Murugi | 2026-05-30 | Completed | Yes
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendies | Key Discussion Points | Next Steps
2026-05-28 | REST API Assignment Planning | Emna Barezi | Moreen Muthoni Murugi & Emna Barezi | Divided tasks — Emna handles API development and DSA, Moreen handles documentation and report | Complete coding, testing and submit by May 30 2026
[Date] |  | [Name] |  | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] |  | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] |  | [Summary of Discussion] | [Follow-up Actions]
[Date] |  | [Name] |  | [Summary of Discussion] | [Follow-up Actions]